## Skills Inventory
Skills
Skills | Team member Name
Apex,Visualforce,C,Java,Python,Mysql | KrishnaSaiReddy Patil
Python,R,C,Embedded C | Aman Geetey
Python,R,Mysql,Jupyter notebooks,Anaconda | Pranav Jaipurkar
C,C++,Python | Yili Zhang
C,C++,Perl,Java | Vijayadhaarani Vijayaarunachalam
Python,C,Java | Tigist Shibeshi

## Team Operating Procedures
Team Operating Procedures
How will the team communicate? | Slack, Whatsapp, Gmail
How often? | Will update daily progress on Slack
Meeting frequency and times? | Twice in a week (Tuesday:1-3 pm, Friday:4-6 pm)
How will the team collaborate? | Github, G-suite, sharing the access request to edit/modify documents.
How are decisions made? | Weighing the evidences, considering trade off betwwen skills, learnability, operational time and going by majority.
How are decisions documented? | Word,Excel
…

## Roles and Responsibilities
Roles and Responsibilities
Role Title | Team Member Name (Primary, Backup) | Responsibilities
Project Manager | KrishnaSaiReddy Patil (Primary), Vijayadhaarani (Backup) | Create a clear and concise plan to execute the project and make sure all software artifacts are completed and submitted with in the deadline.Serve as the main point of communication with the instructors and the team. Maintain healthy work environment in the group. Monitor the progress and efficiently take the corrective measures.Collects effort from team members and generate records in the tracking sheet.Identify the risks in advance and take necessary actions.
Requirements Lead | Pranav (Primary), Vijayadhaarani (Backup) | Creating a well planned operating strategy for drafting utility tree, abuse case diagram, context model, use case diagram, abuse case description, and deriving a list of requirements from the use case and abuse case diagrams. Making efforts to distribute the work evenly among all team members, have a good collaboration strategy and having a good reviewing plan so that mistakes made by team members can be rectified before the document submission.
UI lead | Aman Geetey (Primary), Pranav (Backup) | Making a comprehensive UI covering and making timely plan as to how the UI should look, for example, given the featuresAlso ensuring UI fits the need of all the three personas. Ensuring a smooth intergration with the backend system.Take the lead in learning JavaScript and Vue and try to get others upto speed
Architecture lead | Vijayadhaarani(Primary), Yili (Backup) | Coordinate discussions regarding the architecture of the system. Coordinate design and documentation of the architecture of the system and submit the Architecture document.
Detailed Design lead | Yili (Primary), Vijayadhaarani (Backup) | The detailed design lead should specify each module's interface, induced from the architecture model. He/she should specify the constraint on the use of such interface. He/she should identify the pre-conditions and post-conditions for each modules. He/she should figure out the responsibilities of each modules as precise as possible. He/she should figure out what design pattern, or data structures and algorithms should be applied to fulfill the functions. He/she should keep detailed traceability table from requirment analysis, UI design, and architecure design.
Implementation Lead | Pranav (Primary), Krishna (Backup) | Compile and analyze data, processes, and codes to troubleshoot problems and identify areas for improvement. Collaborating with the front-end developers and other team members to establish objectives and design more functional, cohesive codes to enhance the user experience.
Test Lead | Tigist (Primary), Aman (Backup) | Coordinate development, documentation, and execution of system test cases. Submit test cases, organize status report and update project manager about progress of testing activities.
…

## Project Enviroment
Project Tools/Development Environment
Management/Collaboration/Communication Activity | Selected Tool(s)
Communication & Management | Whats app and Slack
Collaboration | Gmail, Google Drive and Github
Engineering Activity | Selected Tool(s)
GUI | Vue, Pencil or Balsamiq
Front end/Back end | Flask, Pycharm
Model Diagrams | Lucid chart
Documentation | Microsoft Word, Microsoft Excel
Database | PostgreSQL
Server | AWS

## Effort Estimation and Tracking
Effort (Person hours)
MAIN ACTIVITY | Sub-tasks | Aman |  | Pranav |  | krishna |  | Dhaarani |  | Tigist |  | Yili |  | TOTAL ESTIMATED EFFORT per task or activity | TOTAL ACTUAL EFFORT per task or activity
|  | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual
Requirements analysis
| Utility Tree & Use Case Diagram | 2 | 1 | 2 | 4 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 12 | 11
| Abuse case diagram & description | 2 | 3 | 2 | 3 | 2 | 1 | 3 | 1 | 3 | 1 | 2 | 4 | 14 | 13
| Context Model, Features list | 2 | 2 | 2 | 1 | 2 | 3 | 3 | 4 | 3 | 2 | 2 | 1 | 14 | 13
Ux modeling
| User Model | 2 | 1 | 3 | 2 | 3 | 2 | 3 | 2 | 4 | 1 | 4 | 1 | 19 | 9
| UI FlowModel | 3 | 2 | 3 | 4 | 4 | 2 | 2 | 2.5 | 4 | 1 | 4 | 1.5 | 20 | 13
| UI Prototype | 4 | 5 | 4 | 1 | 4 | 4 | 3 | 3 | 5 | 1 | 4 | 3 | 24 | 17
Architecture design
| Architecture Drivers and Decisions | 3 | 4 | 5 | 7 | 4 | 7 | 4 | 8 | 3 | 3 | 4 | 4 | 23 | 33
| Architecture Views | 4 | 4 | 4 | 7 | 3 | 10 | 5 | 10 | 3 | 3 | 3 | 4 | 22 | 38
| Architecture Behavior | 4 | 5 | 5 | 6 | 3 | 5 | 4 | 5 | 2 | 2 | 5 | 5 | 23 | 28
| Documentation | 2 | 3 | 2 | 4 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 1 | 13 | 15
Detailed design
| Detailed design structure | 4 | 3 | 5 | 6 | 4 | 4 | 5 | 3 | 3 | 3 | 5 | 4 | 26 | 23
| Detailed design behavior | 4 | 2 | 4 | 5 | 4 | 4 | 4 | 3 | 3 | 2 | 5 | 3 | 24 | 19
| Design principles & Patterns | 3 | 3 | 3 | 4 | 3 | 3 | 4 | 4 | 2 | 1 | 3 | 1 | 18 | 16
Implementation
| Code & Compile | 20 | 30 | 25 | 25 | 20 | 30 | 20 | 35 | 20 | 4 | 20 | 7 | 125 | 131
| Documentation | 5 | 5 | 4 | 4 | 3 | 2 | 3 | 3 | 2 | 1 | 3 | 2 | 20 | 17
| Code Review | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 3 | 1 | 4 | 3 | 26 | 22
Testing
| Unit Testing | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 5 | 3 | 4 | 3 | 1 | 15 | 16
| Interface Testing | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 3 | 4 | 4 | 1 | 16 | 13
| System & Performance Testing | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 3 | 3 | 3 | 1 | 15 | 12
Project management |  | 2 | 2 | 2 | 2 | 8 | 8 | 4 | 4 | 1 | 1 | 1 | 1 | 18 | 18
TOTAL ESTIMATED and ACTUAL EFFORT per student |  | 77 | 86 | 86 | 96 | 82 | 99 | 84 | 105.5 | 75 | 41 | 83 | 49.5 | 487 | 477

## Risk Analysis and Management
Risk Analysis and Management
Risk description | Probability (Low=1, Medium=2, High=3) | Impact (Low=1, Medium=2, High=3) | Score (Probability x Impact) | Top 5 Priority Risks | Prevention or Mitigation actions
Technical Risk |  |  |  | Unfamiliarity with Java Script | Scale up on Javascript and assist others
Unfamiliarity with Java Script | 2 | 3 | 6 | Miscommunication | Document and share minutes of meeting to ensure everyone has same level of understanding
Integration Risk | 1 | 3 | 3 | Error-prone,unmanageable code | Write optimized code and perform code reviews
Error-prone,Unmanageable code | 2 | 2 | 4 | Availability of team member | Having a backup for every member in case team member is unavailble due to unforeseen circumstances
Insufficient testing | 1 | 2 | 2 | Deadline Overlap | Effective Time Management
Management Risk
Team Communication | 2 | 2 | 4
Availability of team member | 2 | 2 | 4
Team member dropping out due to unforeseen circumstances | 1 | 2 | 2
People Risk
Miscommunication | 2 | 3 | 6
Deadline Overlap | 2 | 2 | 4
Unforeseen health problems | 1 | 2 | 2

## Lessons Learnt
Activity | What worked well and you would repeat in a future project? | What didn’t work well and what would you do differently about it in a future project?
Requirements Analysis | Listing down the features and drafting the utility tree,abuse and use case diagram made us think about all the possible problems/features our system will have and plan in advance on how those features can be implemented or risk mitigation. Brainstorming session played a vital role in finalizing decisions. Looking at all the possible options, planning in advance and brainstorming to finalize decisions have worked well and would like to repeat going forward | Didn’t face much issues as entire week went smooth, but would like to improve time management and co-ordination between team members by making effective use of time as all of them are enrolled in different subjects and work somewhere, so availabilty of all team memebers at a same time needs to be well planned in advance
UCD (Ux modeling) | Discovering the persona and developing wireframe using balsamiq. Learned that a very consistent UI flow diagram can lead us to a better and more organised UI. Also saw how drawing wireframes could simplify so many doubts and could tell us what we may need to correct in our UI flow and how those ratifications may seem more obvious. | Should have spent more time in storyboards. We missed deriving requiremnets from personas drafted. The workload was a bit too much in this one, at least more than what we anticipated. Will work towards making a basic UI (wireframe) and a starting UI flow model early in the project so that we have some base to build.
Architecture design | Gave us an opportunity to explore multiple architectural styles and how well they fit with our product. While defining db schema we had to think in depth of every relationship and attributes. sequential diagrams gave us a clear picture of how the interface flow works. Overall it was a good learning phase and made us visualise all the requirements which we had gathered and how the product is gonna be. | Maintaining consistency among logical view, deployment view, behavioural view, sequential diagrams and other UML diagrams between all team members was a bit challenging. Describing the interfaces that components provided and the interfaces that component required in logical view and maintaining same consistency in component description was a bit challenging. Moreover, we also found out that we need to keep the interface descriptions in specific orders or else there was a risk of missing an interface description in the document.
Detailed design | Detailed design structure and behavior have helped us to think in depth and visiualize the product and have helped us to identify classes and methods which would ease our work during impelmentation. After creating UML class diagrams we were able to see Fascade and Single responsibility patterns implemented to particular classes from the diagram itself which helped us know that we were on a right track. | Took lot of time in figuring out most of the things as they were new for us, It was challenging to maintain consistency but we were able to figure out in the end and this would help us during implementation. We had some doubts as to what was exactly expected in the algorithms section i.e. whether it was psedo code or a flowchart or something else. But prompt reply by our TAs helped us to complete that section.
Implementation | Implementation task gave us an idea about what actually software development is. Moreover storing data in the database,querying to access the data and learning about integration of Pycharm with PostgreSQL were some of the things that went pretty well for this task. | The fact that all the team members were not experienced in building web application before was one of the major drawback which impacted our performance. Moreover, there was no technology which was unanimously mastered by all the members, hence it was difficult for some of the members as they had to start from the beginning. Moreover, lack of time management was also a major loophole for this task in our project.
Testing | Unit testing helped us to fix issues before integrating it with other components. Testing also helped us to discover scenarios that we missed during implementation, like displaying what went wrong to the user in addition to handling it. | Since implemenation took more time than expected, we didn't find enough time to run more number of test cases
Project management | We mastered Risk mitigation, Over the semester there were many instances where some of the resources were sick and some couldn't actively contribute to the project but we still managed to deliver on time as we anticipated in advance and were planned accordingly for such situations. | Since most of us didn't had a common skill it was bit tough figuring out a technology to start working on and later many couldn't scale up to an extent so they had faced issues during implementation. we could've choosen a different technology or an additional effort from individuals could've resulted in a better product